## Defects
SI No | Submitted Date | Description | Sprint | Assigned To | Defect Type | Action Taken | Action Taken Date | Status | Remarks
1 | 2025-09-23 | OCR not extracting Patient_ID | Sprint 1 | Backend Team | Functional | Improved preprocessing, added configs | 2025-09-24 | Closed | Improved
2 | 2025-10-08 | ICD-10 mapping inconsistencies | Sprint 2 | AI Team | Algorithmic | Improved ICD-10 matching | 2025-10-09 | Closed | Better accuracy
3 | 2025-10-10 | MRI images not displaying | Sprint 2 | Frontend Team | UI/Integration | Fixed paths + API | 2025-10-11 | Closed | Verified
4 | 2025-10-12 | MRI caption repetitive | Sprint 2 | AI Team | Model Training | Fixed decoding | 2025-10-13 | Closed | Stable output
5 | 2025-10-22 | Duplicate Patient_ID |  | Backend | Logic | UUID + duplicate rules | 2025-10-23 | Closed | Unique IDs
6 | 2025-10-25 | MRI uploads rejected | Sprint 3 | Frontend | UI/Validation | MIME validation | 2025-10-26 | Closed | Working
7 | 2025-10-27 | Slow summarization pipeline | Sprint 3 | AI Team | Performance | GPU + batching | 2025-10-28 | Closed | Faster
8 | 2025-11-05 | Reports not updating | Sprint 4 | Backend | Integration | Remapped schema | 2025-11-06 | Closed | Synced
9 | 2025-11-07 | ICD-10 missing in reports | Sprint 4 | Frontend | Functional | Fixed binding | 2025-11-08 | Closed | Correct output
10 | 2025-11-10 | MRI images missing | Sprint 4 | Backend | UI | Fixed PIL rendering | 2025-11-11 | Closed | Shows correctly

## Sheet2
Logical
User Interface
Maintainability
Standards
Others