## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
Sprint 1 | Sprint 1 | US001 | As a doctor, I want to upload medical images so that the AI can enhance and process them. | Must Have | Image upload module | Frontend Team | Completed
Sprint 1 | Sprint 1 | US002 | As an AI engineer, I want to integrate the image enhancement model so that doctors receive clearer visual outputs. | Must Have | Model availability | Backend Team | Completed
Sprint 2 | Sprint 2 | US003 | As a clinician, I want to enter patient clinical notes so that the AI can generate structured medical summaries. | Must Have | Text input form | Frontend Team | Completed
Sprint 2 | Sprint 2 | US004 | As an AI developer, I want the system to automatically generate ICD-10 codes so that diagnoses are standardized. | Should Have | Clinical summary output | Backend Team | Completed
Sprint 3 | Sprint 3 | US005 | As a UI/UX designer, I want to create a clean and simple interface so that doctors can easily use the system. | Must Have | Backend API | Frontend Team | Completed
Sprint 3 | Sprint 3 | US006 | As a backend engineer, I want to build API endpoints for image enhancement, report generation, and ICD-10 inference. | Must Have | AI model integration | Backend Team | Completed
Sprint 4 | Sprint 4 | US007 | As a DevOps engineer, I want to deploy the entire application online so that it can be accessed from any device. | Could Have | Frontend & backend integration | DevOps Team | Completed
Sprint 4 | Sprint 4 | US008 | As a QA tester, I want to validate all modules so that the system is reliable and error-free. | Should Have | Fully integrated system | QA Team | Completed
Sprint 4 | Sprint 4 | US009 | As a technical writer, I want to prepare complete project documentation so that stakeholders can understand the system. | Must Have | Finalized features | Documentation Team | Completed