## Sheet1
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | 1 | 2025-09-22 | 2025-10-06 | Backend Team | Define clear preprocessing pipeline for medical images | Running inference without validating image quality | Synchronizing frequently with AI team | Created standardized preprocessing workflow with documentation
2 | 2 | 2025-10-07 | 2025-10-20 | AI Team | Validate clinical summaries with sample clinician feedback | Using generic summarization prompts | Iteratively tuning the summarization model | Developed medically‑aligned prompt templates and validation rules
3 | 3 | 2025-10-21 | 2025-11-03 | AI + Backend Team | Optimize ICD‑10 model with confidence scoring | Using single-label predictions only | Monitoring inference logs for model accuracy | Implemented multi‑label ICD‑10 inference with thresholding
4 | 4 | 2025-11-04 | 2025-11-17 | Frontend + Backend | Coordinate API–UI integration earlier in the sprint | Waiting until end of sprint to integrate enhancement outputs | Maintaining consistent API–UI contract | Scheduled mid‑sprint integration checkpoints
5 | 5 | 2025-11-18 | 2025-11-22 | DevOps + Full Team | Automate deployment and testing workflows | Manual environment testing | Continuous monitoring of deployed system | Added CI/CD with auto‑tests, improved deployment reliability