## Sheet1
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
US001 | T1 | Design and implement image upload module | 2025-09-22 | 2025-09-23 | Frontend1 | UI Development | Done | 6 | bar: Day 1 to Day 2
US001 | T2 | Integrate AI image enhancement model API | 2025-09-22 | 2025-09-24 | Backend1 | Model Integration | Done | 10 | bar: Day 2 to Day 4
US002 | T3 | Develop clinical text input & preprocessing module | 2025-09-22 | 2025-09-25 | Frontend2 | UI Development | Done | 12 | bar: Day 3 to Day 6
US003 | T4 | Implement ICD-10 classification pipeline | 2025-10-07 | 2025-10-10 | Backend2 | AI Inference | Done | 8 | bar: Day 4 to Day 6
US004 | T5 | Create output UI for enhanced images and reports | 2025-10-07 | 2025-10-10 | Frontend3 | UI/UX | Done | 10 | bar: Day 5 to Day 8
US005 | T6 | Deploy frontend and backend | 2025-10-21 | 2025-10-23 | DevOps | Deployment | Done | 8 | bar: Day 6 to Day 9