## Standup_Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | Day 2 | Image enhancement model output blurry for low-light radiology images | Added preprocessing (contrast normalization + histogram equalization)
Sprint 1 | Day 4 | Backend API returning slow responses during image enhancement inference | Enabled model warm‑loading and optimized CUDA batch size
Sprint 2 | Day 3 | Clinical summary generation occasionally missing key symptoms from clinician notes | Improved text preprocessing and added medical keyword extraction
Sprint 2 | Day 5 | ICD‑10 code prediction giving low‑confidence outputs for multi‑disease cases | Added confidence thresholding and fallback multi‑label classification rule
Sprint 3 | Day 2 | Frontend UI failing to display enhanced images due to incorrect base64 formatting | Fixed decoder handling and updated API response structure
Sprint 3 | Day 4 | Users reporting long wait time when summary + ICD‑10 tasks run together | Separated tasks into async workers using queue-based processing
Sprint 4 | Day 1 | Deployment build failing because of incompatible Python dependency versions | Pinned stable versions and rebuilt using isolated virtual environment
Sprint 4 | Day 3 | Doctors unable to upload large DICOM files on UI | Increased upload size limit and implemented progressive uploading